## Backlog
id | Story | Note | Estimate | Status | Priority | Sprint#
General
0a | Create SQL script for quick restore db schema
0b | Create git repository for project
0c | Configure environment
0d | Write log system |  |  |  |  | #2
Admin
1 | I as the admin want to have possibility add user into system
2 | I as the admin of the system want to have possibility edit users into system
3 | I as the admin of the system want to have possibility remove users into system
4 | I as the admin of the system want to have possibility send notiffication on email for users into system
26 | I as the admin of the system want to have possibility search users by keyword
Manager
5 | I as the manager of the system want to have possibility view newest issues |  |  | Done
6 | I as the manager of the system want to have possibility view all issues on my toolpage |  |  | Done |  | #3
7 | I as the manager of the system want to have possibility search issue by something paremeters |  |  |  |  | #4
8 | I as the manager of the system want to have possibility quick change issue status from my manager toolpage |  |  | Done |  | #3
9 | I as the manager of the system want to have possibility edit issue from my manager toolpage |  |  |  |  | #3
10 | I as the manager of the system want to have possibility delete issue from my manager toolpage
11 | I as the manager of the system want to have possibility manage issue category from my manager toolpage |  |  |  |  | #3
12 | I as the manager of the system want to have possibility quick change issue category from my manager toolpage |  |  | Done |  | #3
29 | I as the user of the manager want to have possibility using filters for issues
30
User
13 | I as the user of the system want to have possibility add new issue into system |  |  | Done? |  | #2
14 | I as the user of the system want to have possibility share issue in social networks
15 | I as the user of the system want to have possibility add comment to any issue in the system
16 | I as the user of the system want to have possibility add issue category if she does not exist
17 | I as the user of the system want to have possibility send notification to manager about resolving some issue
18 | I as the user of the system want to have possibility view details about some issue |  |  | Done |  | #3
19 | I as the user of the system want to have possibility subscribe on some issue
20 | I as the user of the system want to have possibility view statistic about resolving issues
21 | I as the user of the system want to have possibility login in the system |  |  | Done? |  | #2
22 | I as the user of the system want to have possibility view all issue on the map
23 | I as the user of the system want to have possibility view confirmation or notiffication windows on my any actions
25 | I as the user of the system want to have possibility use filter for issues
26 | I as the user of the system want to have possibility view my profile page |  |  | Done? |  | #2
27 | I as the user of the system want to wave possibility change my avatar
28 | I as the user of the system want to have possibility register in the system |  |  | Done? |  | #2

## Sprint#1
id | Story | Note | Estimate, h | Status | Priority | Assign | Start day | 2015-06-12 | End day | 2015-06-26 | 40 | 240
General
1 | I as the user of the system want to have possibility sign in into system
1.1 | Create login form |  | 2
1.2 | Write stylesheet for form according to mockup |  | 16
1.3 | Write validation function for login fields |  | 8
1.4 | Add possibility for login with social networks | Google+, Facebook | 24
1.5 | testing
1.6 | bugfixing
2 | I as the user of the system want to have possibility sign up into system
2.1 | Create sign up form |  | 2
2.2 | Write stylesheet for form according to mockup |  | 16
2.3 | Write validation function for sign up fields | Email: .@-_zZ1 Password: >6, kK&1 | 8
2.4 | Add possibility for signup with social networks | Google+, Facebook | 24
2.5 | testing
2.6 | bugfixing
3 | I as the user of the system want to have possibility view main page
3.1 | Create main page for system according to mockup |  | 8
3.2 | Include map api on to main page | Googlemap or OpenStreetMAp | 16
3.3 | Write stylesheet for main page | Bootstrap make responsive, use less | 24
4 | I as the user of the system want to have possibility add pointer on the map
4.1 | write JS function for getting coordinate points by click on the map |  | 16
|  |  | 164 | 76

## Sprint#2
id | Story | Note | Estimate, h | Status | Priority | Assign | Start day | 2015-06-26 | End day | 2015-07-13 | 240
0d | Write log system | Log levels: - Warning; - Error; - Info; - Debug; | 20
User
13 | I as the user of the system want to have possibility add new issue into system
13.1 | Implement method for adding new issue into db with server side |  | 8
13.2 | Implement method for sending data about new issue to server side from client |  | 13
13.3 | Implement notiffication status about succesefull | add or error | 5
13.4 | Provide validation of data | Server side and client side | 8
13.5 | Implement view for adding issue into system |  | 8
13.6 | Testing |  | 10
13.7 | Bugfixind |  | 10
21 | I as the user of the system want to have possibility login in the system
21.1 | Implement method for login into the system from client side |  | 13
21.2 | Implement method for login into the system on server side |  | 20
21.3 | Implement view for login page |  | 2
21.4 | Redirect to main page with link on his proffile |  | 2
21.5 | Provide validation of user data |  | 3
21.6 | Testing |  | 10
21.7 | Bugfixind |  | 10
28 | I as the user of the system want to have possibility register in the system
28.1 | Implement method for register into the system from client side |  | 8
28.2 | Implement method for register into the system on server side |  | 20
28.3 | Implement view for register page |  | 2
28.4 | Implement method for sending confirmation link on email |  | 5
28.5 | Provide validation of user data |  | 1
28.6 | Testing |  | 10
28.7 | Bugfixind |  | 10
26 | I as the user of the system want to have possibility view my profile page
26.1 | Implement view for proffile page |  | 8
26.2 | Implement method for edit proffile page |  | 8
26.3 | Testing |  | 10
26.4 | Bugfixind |  | 10
Techical tasks
x.1 | Install Database server |  | 0
x.2 | Write SQL script for creating database |  | 5
x.3 | Install Laravel and dependences |  | 1 | 0

## Sprint#3
id | Story | Note | Estimate, h | Status | Priority | Assign | Start day | 2015-07-17 | End day | 2015-08-05 | 240
0d | Write log system | Log levels: - Warning; - Error; - Info; - Debug; | 20
User
17 | I as the user of the system want to have possibility send notification to manager about resolving some issue
| Add button "Resolve" on view "Detail issue" |  |  | Done
implement method for change status issue on "To Resolve"
Inmplement notification window
Testing
bugfixing
18 | I as the user of the system want to have possibility view details about some issue |  |  | Done
| Inmplement view "Detail issue" |  |  | Done
| Implement method for getting data about some issue |  |  | Done
Testing
bugfixing
Manager
6 | I as the manager of the system want to have possibility view all issues on my toolpage |  |  | Done
| Implement view "Manager toolpage" |  |  | Done
| Implement view for showing all issues | without "Canceled" |  | Done
| Implement method for getting issues data from db |  |  | Done
Testing
bugfixing
8 | I as the manager of the system want to have possibility quick change issue status from my manager toolpage |  |  | Done
| Implement method for update status of issue |  |  | Done
| Implement dropdown lish with all approved statuses |  |  | Done
Testing
bugfixing
9 | I as the manager of the system want to have possibility edit issue from my manager toolpage
| Implement view for editing some issue | modal window or new page |  | Done
| Implement method for update all data about issue |  |  | Done
Implement nottification and comfirmation windows
Implement validation data
Testing
bugfixing
11 | I as the manager of the system want to have possibility manage issue category from my manager toolpage
| Implement view for list of categories |  |  | Done
implement method for add new categories
Implement method for edit some categorie
Implement method for approve some categorie
Implement nottification and confirmation windows
Testing
bugfixing
12 | I as the manager of the system want to have possibility quick change issue category from my manager toolpage |  |  | Done
| Implement method for update category of issue |  |  | Done
| Implement dropdown lish with all approved categories |  |  | Done
Testing
bugfixing

## Sprint#4
id | Story | Note | Estimate, h | Status | Priority | Assign | Start day | 2015-08-21 | End day | 2015-09-03
7 | I as the manager of the system want to have possibility search issue by something paremeters
Add checkboxes to search panel
implement method for search issues by choosen parameters
provide validation data
provide clear result of search
testing
bugfixing
20 | I as the user of the system want to have possibility view statistic about resolving issues | D3.js or Raphaël 1) Issue categories 2) Resolved - Active
Implement sidebar for statistic data
Implement method for getting statistic data
Implent methods for calculate statistic data
testing
bugfixing
1 | I as the admin want to have possibility add user into system
Write HTML for admin toolpage
Create method for add user into db
| Write method for data validation | name, email, password
create method for check exist user into db
Implement notification window
Implement HTML form for add user
testing
bugfixing
2 | I as the admin of the system want to have possibility edit users into system
Create method for edit user into db
Implement HTML form for edit user
Bind button on event for edit user
Implement confirmation window for edit user
Testing
Bugfixing
3 | I as the admin of the system want to have possibility remove users into system
Create method for remove user from db
Implement HTML button for remove user
Bind button on event for remove user
Implement confirmation window for remove user
Testing
Bugfixing